## Sheet1
Course: EPMBA SEM II-OM
Subject: Project Management
Faculty: Prof. Poonam Tellawar
Questions | [7 empty] | Option 1 | Option 2 | Option 3 | Option 4 | Correct Option | Marks | Negative Marks | Test Catagory Code | Test Sub-Catagory Code | Test Lebels Code
Q1)The project life cycle consists of | [7 empty] | (A)Understanding the scope of the project | (B) Objectives of the project | (C)Formulation and planning various activities | (D)All of the above | D |  |  | III-OM | 2018-2019 | EpMBA
Q2) Following is(are) the responsibility(ies) of the project manager. | [7 empty] | (A) Budgeting and cost control | (B) Allocating resources | (C) Tracking project expenditure | (D) All of the above | D
s
Q3) Following are the phases of Project Management Life Cycle. Arrange them in correct order | [7 empty] | (A) 3-2-1-4 | (B) 1-2-3-4 | (C) 2-3-1-4 | (D) 4-3-2-1 | A
1. Design, 2. Marketing, 3. Analysis and evaluation, 4. Inspection, testing and delivery
Q4) Design phase consist of | [7 empty] | (A) Input received | (B) Output received | (C) Both (A) and (B) | (D) None of the above | C
Q5) Project performance consists of | [7 empty] | (A) Time | (B) Cost | (C) Quality | (D) All of the above | D
Q6)-Five dimensions that must be managed on a project | [7 empty] | (A) Constraint, Quality, Cost, Schedule, Staff | (B) Features, Quality, Cost, Schedule, Staff | (C) Features, priority, Cost, Schedule, Staff | (D) Features, Quality, Cost, Schedule, customer | B
Q7)-The entire process of a project may be considered to be made up on number of sub process placed in different stage called the | [7 empty] | (A) Technical key resources | (B) Work key structure | (C) Work Breakdown Structure (WBS). | (D) None of the above | C
Q8).Following is (are) the component(s) of risk management | [7 empty] | (A) Risk Assessment | (B) Risk Control | (C) Risk Ranking | (D) All of the above | D
Q9).-“Devising and maintaining a workable scheme to accomplish the business need” is | [7 empty] | (A) Initiating process | (B) Planning process | (C) Executing process | (D) Controlling process | B
Q10) Which of these is not one of the constraints of a project? | [7 empty] | A)Scope | B) Resources | c)Team | D)Budget | C
Q11)Which of the following is not correct about initial phase of a project? | [7 empty] | A)The cost associated at the beginning of the project is highest. | B) Stakeholders have maximum influence during this phase | C) The highest uncertainty is at this stage of the project | D)All the above statements are correct. | A
Q12) Find Critical Path for given data
Activity |  |  | Preceding Activity |  |  | Duration |  | A.1-2-4-6 | B.1-3-5-6 | C.1-3-5-4-6 | D.1-3-4-6 | C
A |  |  | - |  |  | 4
B |  |  | - |  |  | 6
C |  |  | A |  |  | 8
D |  |  | B |  |  | 7
E |  |  | B |  |  | 4
F |  |  | E |  |  | 5 | 5
G |  |  | E |  |  | 4 | 4
H |  |  | C,D,F |  |  | 5
Q13) What is early start of activity D? | [7 empty] | A.5 | B. 6 | C.4 | D.7 | B
Q14) What is Early Finish of activity G? | [7 empty] | A.14 | B.15 | C.16 | D.17 | A
Q15) What is duration of critical path? | [7 empty] | A.20 | B.22 | C. 26 | D.14 | A
Q16)Delays in one project cause delays in other projects because of…… | [7 empty] | A. Resource Allocation | B.Interdependencies | C. Technological Factor | D. Dependancies | C
Q17) The product, support and integration are types of ……. | [7 empty] | A.Management work | B. Project work | C. Both | D. None | B
Q18) To plan a project, the total scope of work must be: | [7 empty] | A.Identified | B.Subdivided into manageable segments | C.Assigned to individuals responsible to do the work and documented | D.All of above | D
Q19) A …….. contract is a business arrangement in which a project is delivered in a completed state. | [7 empty] | A.Turnkey | B.Non Turnkey | C. Both | D.none of above | A
Q20) They are preferred when projects are small sized, know-how is available. | [7 empty] | A.True | B. False |  |  | D
Q21) In ……………...contract after completion of the work, the contractor is paid by the project promoter at a certain percentage above the actual cost of execution. | [7 empty] | A.Piece work | B.Lumpsum | C. Cost plus | D. None | C
Q22) This type of contract is chosen when the project promoters do not want to compromise on the quality of material.z | [7 empty] | A.Piece work | B.Lumpsum | C. Cost plus | D. None | D
Q23) EMD stands for: | [7 empty] | A.Earnest Monitory Deposit | B. Early Money Deposit | C. Earnest Money Deposit | D. None | C
Q24) Tender evaluation followed by | [7 empty] | A.Bid opening | B.Tender document | C.Press release | D.None | A
Q25) Criteria for accepting tenders: | [7 empty] | A.Financial capacity of the tenderer | B.Technical infrastructure. | C.Past performance of the tenderer | D.All of above | D
Q26) A deliverable oriented grouping of project elements which organizes and defines the total scope of the project. It is referred as | [7 empty] | A.WBS | B. MPS | C. BOM | D. None | A
Q27) In Project Life Cycle the planning phase is followed by | [7 empty] | A. Initiation | B. Executing | C. Monitoring | D. Controlling | B
Q28) Project work is .. | [7 empty] | A.Make to order | B. Build to stock | C. Assemble to order | D.None | A
Q29) The characteristic of project is Constant pressure of conformance to | [7 empty] | A.Time | B.Cost | C. Performance goals | D. All of above | D
Q30) Project works on successive principal. | [7 empty] | A.True | B. False |  |  | A
Q31) The PERT stands for | [7 empty] | A. Project Elimination and Review Technique | B. Project Evaluation and Review Technique | C. Process Elimination and Review Technique | D. Process Evaluation and Review Technique | B
Data for Q32 to Q 36
Activity | Preceding Activity | Duration(Weeks)
|  | a | m | b
A | - | 2 | 4 | 6
B | - | 6 | 6 | 6
C | - | 6 | 12 | 24
D | A | 2 | 5 | 8
E | A | 11 | 14 | 23
F | B,D | 8 | 10 | 12
G | B,D | 3 | 6 | 9
H | C,F | 9 | 15 | 27
I | E | 4 | 10 | 16
Q32) What is the critical path? | [7 empty] | A. A-E-I | B. B-G | C. A-D-F-H | D. C-H | C
Q33) What is duration of critical path? | [7 empty] | A. 33 weeks | B. 35 weeks | C. 35 weeks | D. 41 weeks | B
Q34) What is expected time for activity D? | [7 empty] | A.5 | B. 6 | C.7 | D.4 | A
Q35) What is variance of the project duration? | [7 empty] | A. 5.23 weeks | B. 3 weeks | C. 3.23 weeks | D. 4 weeks | C
Q36) The length of activities c-h is | [7 empty] | A. 29 | B. 32 | C. 15 | D. 31 | A
Q37) Which activity has optimistic, pessimistic and modal time equal? | [7 empty] | A. A | B.B | C.C | D.D | B
Q38) ________ is the application of knowledge, skills, tools and techniques to project activities to meet project requirement. | [7 empty] | A. Project Portfolio Management | B. Project Management | C. RProject Management | RProject Portfolio Management | B
Q39) _____ is the temporary endeavor undertaken to create unique product, service or result. | [7 empty] | A. Program | B. Process | C. Project | D. Portfolio | C
Q40) Which characteristic distinguish a project from normal operation? | [7 empty] | A. Produces benefits | B. Carries more risks | C. Delivers Products | D. Incurs cost | B
Q41) Which is characteristic of project? | [7 empty] | A. Low risk | B. Avoid stress and strain between organization | C. Business as usual | D. Cross Functional | D
Q42) Which of the following types of organizational charts can be BEST used to track project? | [7 empty] | A. Organizational Breakdown Structure | B. Responsibility Assignment Matrix | C. BCG Matrix | D. Resource Breakdown Structure | D
Q43) Problem of changing scope or performance expected of a project is a major___ | [7 empty] | A. Issue | B. Drawback | C. Success | D. Downfall | A
Q44) Cause of change that cannot be managed by PM is_ | [7 empty] | A. Technological Uncertainty | B. Innovation | C. Change in environment | D. Increased client knowledge | C
Q45) A project is ongoing repetitive work effort that follows existing organizational procedures. | [7 empty] | A-True | B-False |  |  | B
Q46) PERT is probabilistic in nature. | [7 empty] | A-True | B-False |  |  | A
Q47) CPM is deterministic in nature. | [7 empty] | A-True | B-False |  |  | A
Q48) __________ is letter issued to successful tenderer about his offer being accepted. | [7 empty] | A. Letter of Credit | B. Letter of Intent | C. Bill Of Credit | D. None | B
Q49) Acting as liaison between suppliers and companies role of_____ | [7 empty] | A. Project Manager | B. Material Manager | C. Both | D. None | B
Q50) A company’s channel decision directly affects | [7 empty] | . A. Channel member | B .Marketing decision | C. Employees | D. Customer’s choice | B
Q51) _________is an organized methodology used to split an overall project into non overlapping components . | [7 empty] | A. WBS | B. CBS | C. OBS | D. None | A
Q52) In project crashing, the normal cost and crash cost are equal. | [7 empty] | A-True | B-False |  |  | B
Q53) By crashing a particular activity we reduce cost and duration of project. | [7 empty] | A-True | B-False |  |  | B
Q54) The cost incurred for rent, material handling, wages etc is termed as | [7 empty] | A. Fixed cost | B. Indirect cost | C. Direct cost | D. None | B
Data for Q55 to Q60 Indirect cost= 105 lacs/month
| Preceding | Nt | Nc | Ct | Cc
| Activity | (Weeks) | (Lacs) | (Weeks) | (Lacs)
Activity
A | - | 3 | 50 | 2 | 100
B | - | 2 | 75 | 1 | 150
C | - | 6 | 140 | 4 | 260
D | A | 5 | 100 | 3 | 180
E | A | 8 | 115 | 6 | 175
F | B | 2 | 80 | 2 | 80
G | C,D,F | 4 | 100 | 2 | 240
Q55) What is total normal cost? | [7 empty] | A. 301 lacs | B. 660 lacs | C. 630 lacs | D. 600 lacs | B
Q56) What is duration of critical path? | [7 empty] | A. 12 | B. 22 | C. 10 | D. 8 | A
Q57) Numbers of paths in mentioned data are | [7 empty] | A. 5 | B. 2 | C. 4 | D. 3 | C
Q58) Indirect cost for the project without crashing any activity is | [7 empty] | A. 1145 | B. 1272 | C. 1260 | D. 1142 | C
Q59) Which of the given activities cannot be crashed? | [7 empty] | A. F | B. B | C. A | D. G | A
Q60) Activity E can be crashed by ______ weeks. | [7 empty] | A. 1 | B. 4 | C. 3 | D. 2 | D